Calorie Tracker

v1 Build & Launch Plan

Day-by-Day Task Checklist

Solo developer · React Native + Expo · Supabase · iOS + Android

30 working days · 6 weeks · One task list per day

WEEK 1 — SETUP & FOUNDATIONS

Day 1 of 30

- Install Node.js

- Install VS Code

- Install Expo CLI (npx create-expo-app)

- Install Expo Go app on your phone

- Create a Supabase project

- Enable Supabase Authentication (Email/Password)

- Create Postgres tables (profiles, food_entries)

- Register for Google Play Developer account

- Register for Apple Developer Program (approval can take 24–48 hrs — start early)

- Create a free Expo account (needed for EAS Build later)

Notes:

WEEK 1 — SETUP & FOUNDATIONS

Day 2 of 30

- Scaffold the Expo project

- Set up navigation (react-navigation)

- Install @supabase/supabase-js

- Connect Supabase client to your Supabase project (URL + anon key)

- Confirm you can scan the QR code and see the app live on your phone

Notes:

WEEK 1 — SETUP & FOUNDATIONS

Day 3 of 30

- Build login/signup screen UI

- Implement email + password sign-in via Firebase Auth

- Implement email + password sign-up via Firebase Auth

- Wire up auth state using Context API

Notes:

WEEK 1 — SETUP & FOUNDATIONS

Day 4 of 30

- Build bottom-tab navigation (Home / Add Food / Reports / Settings)

- Write SQL to create the profiles table

- Write SQL to create the food_entries table

- Enable Row Level Security policies so users only see their own data

Notes:

WEEK 1 — SETUP & FOUNDATIONS

Day 5 of 30

- Test full auth flow live on your phone via Expo Go

- Fix any bugs found (buffer day)

Notes:

WEEK 2 — FOOD LOGGING CORE

Day 6 of 30

- Integrate USDA FoodData Central API

- Build search function against the API

- Parse and structure the API response

Notes:

WEEK 2 — FOOD LOGGING CORE

Day 7 of 30

- Integrate Open Food Facts API

- Merge results from both APIs

- Display combined results

Notes:

WEEK 2 — FOOD LOGGING CORE

Day 8 of 30

- Build food search UI

- Build results list component

- Display calorie info per result

Notes:

WEEK 2 — FOOD LOGGING CORE

Day 9 of 30

- Build 'add entry' flow UI

- Add quantity input field

- Insert entry into food_entries table with user_id + timestamp

Notes:

WEEK 2 — FOOD LOGGING CORE

Day 10 of 30

- Test search + add flow live on your phone

- Fix bugs found during testing

Notes:

WEEK 3 — DASHBOARD & REPORTS

Day 11 of 30

- Build daily dashboard UI

- Query today's entries from food_entries table

- Display running calorie total

Notes:

WEEK 3 — DASHBOARD & REPORTS

Day 12 of 30

- Add daily goal setting UI

- Add progress bar showing total vs. goal

Notes:

WEEK 3 — DASHBOARD & REPORTS

Day 13 of 30

- Build weekly report screen

- Query food_entries for last 7 days

- Group entries by day

Notes:

WEEK 3 — DASHBOARD & REPORTS

Day 14 of 30

- Integrate react-native-chart-kit

- Render weekly bar chart from grouped data

Notes:

WEEK 3 — DASHBOARD & REPORTS

Day 15 of 30

- Test dashboard and reports screens

- Optimize any slow Firestore queries

Notes:

WEEK 4 — SETTINGS, POLISH, EDGE CASES

Day 16 of 30

- Build settings screen UI

- Implement edit-goal functionality

- Implement logout functionality

- Implement delete-account functionality (required by Apple)

Notes:

WEEK 4 — SETTINGS, POLISH, EDGE CASES

Day 17 of 30

- Handle no-internet state gracefully

- Add empty-state UI for no entries

- Add loading-state UI

- Add error messages for failed API/Firestore calls

Notes:

WEEK 4 — SETTINGS, POLISH, EDGE CASES

Day 18 of 30

- Apply consistent theme/styling across app

- Design and add app icon

- Design and add splash screen

Notes:

WEEK 4 — SETTINGS, POLISH, EDGE CASES

Day 19 of 30

- Run performance pass on real devices

- Check for UI jank or unnecessary re-renders

- Fix any performance issues found

Notes:

WEEK 4 — SETTINGS, POLISH, EDGE CASES

Day 20 of 30

- Do a full manual QA run — use the app for a real day

- Log real food entries

- Catch and note bugs for fixing

Notes:

WEEK 5 — STORE PREPARATION

Day 21 of 30

- Write privacy policy

- Host privacy policy (e.g. GitHub Pages)

- Draft Play Console Data Safety form answers

Notes:

WEEK 5 — STORE PREPARATION

Day 22 of 30

- Prepare Play Store app icon

- Prepare Play Store screenshots

- Write Play Store description

- Complete content rating questionnaire

Notes:

WEEK 5 — STORE PREPARATION

Day 23 of 30

- Prepare App Store screenshots (multiple device sizes)

- Complete App Privacy 'nutrition label' in App Store Connect

- Write App Store description and keywords

Notes:

WEEK 5 — STORE PREPARATION

Day 24 of 30

- Configure eas.json

- Run EAS Build for Android (.aab)

- Run EAS Build for iOS (.ipa)

Notes:

WEEK 5 — STORE PREPARATION

Day 25 of 30

- Submit Android build to Google Play internal testing track

- Submit iOS build to Apple TestFlight

Notes:

WEEK 6 — TESTING & LAUNCH

Day 26 of 30

- Collect feedback from internal testers

- Fix critical bugs found (part 1)

Notes:

WEEK 6 — TESTING & LAUNCH

Day 27 of 30

- Continue fixing bugs found in internal testing (part 2)

- Re-test fixes

Notes:

WEEK 6 — TESTING & LAUNCH

Day 28 of 30

- Promote Android build toward production release

- Submit iOS build for official App Store review

Notes:

WEEK 6 — TESTING & LAUNCH

Day 29 of 30

- Buffer day — monitor Apple review status

- Respond to any requested changes from Apple

Notes:

WEEK 6 — TESTING & LAUNCH

Day 30 of 30

- Publicly release app on Google Play

- Publicly release app on Apple App Store

- Monitor Sentry closely for the first 48 hours

Notes: